## Worksheet
Schedule ID | Building Trade | Trade Category | Strategic Partner | Frequency | Description | Type | Scope | Site | Building | Floor | Room | No of Day(s) Before to Notify | Start Date | End Date | Exclude | Work Started Date | Work Completed Date | Attended By | Portal ID | Service Report Completed Date | Total Number of Service Reports | Total Number of Quantity in Service Reports | Asset Tag Number | Alert Case
3217 | Building | Building External Surfaces | Test Company | Once | D&B Kingfisher Wetland - Permit to Work (Tehc) | Building | Construction Works | Gardens By The Bay (South) | Other Outdoor Area |  |  | 1 | 2021-06-12 | 2021-11-30 |  | 2021-06-17 11:34:31 | 2021-06-17 11:34:48 | Kashvin Kaur |  |  | 0 | 0
3245 | Building | Building External Surfaces | Test Company | Once | Renovation of Pollen Restaurant by Foundry K | Building | Renovation | Gardens By The Bay (South) | Satay by the Garden |  |  | 1 | 2021-06-28 | 2021-10-15 |  | 2021-10-09 14:39:23 | 2021-10-09 14:40:38 | Kashvin Kaur |  |  | 0 | 0
3301 | Electrical | Light Switches | Test Company |  | To turn on the lights of Porsche at Lattice at 6.45pm & turn off at 10pm | Electrical | Switches | Gardens By The Bay (South) | Floral Fantasy |  |  |  | 2021-06-28 | 2021-12-31 | [6 empty] | 0 | 0
3800 | Events | Power Handover | Test Company |  | [All Day]Work Site Location for MAF 2021 Bayfront Plaza Carpark | Events | Work Site | Gardens By The Bay (South) | Bayfront |  |  |  | 2021-08-05 | 2021-10-15 |  | 2021-10-16 10:43:02 | 2021-10-16 10:43:16 | Kashvin Kaur |  |  | 0 | 0
3909 | Building | PA | Test Company |  | [9am-11.50pm]Adventure Singapore-MAF Livestream Installation at Flower Field Hall | Building | Installation | Gardens By The Bay (South) | Flower Dome |  |  |  | 2021-09-13 | 2021-10-02 |  | 2021-10-04 11:47:43 | 2021-10-04 11:56:02 | Kashvin Kaur |  |  | 0 | 0
3997 | Events | Photoshoot / Media Press | Test Company |  | [10am-12am]Mid Autumn Festival performance show at FFH | Events | Performance | Gardens By The Bay (South) | Flower Dome |  |  |  | 2021-09-15 | 2021-10-02 |  | 2021-10-04 11:46:50 | 2021-10-04 11:47:08 | Kashvin Kaur |  |  | 0 | 0
4013 | Cleaning | Exterior | BNL Pte Ltd |  | [8am-7pm]BNL - Façade cleaning at Floral Fantasy | Cleaning | Façade | Gardens By The Bay (South) | Floral Fantasy |  |  |  | 2021-09-27 | 2021-10-04 |  | 2021-10-05 13:42:18 | 2021-10-05 13:43:26 | Kashvin Kaur |  |  | 0 | 0
4015 | Mechanical | Lift System | Test Company |  | [9am-6pm]Full load test and inspection for Escalators and lifts for the application of Permit to Operate at FD, CF, Arrival & Canopy Hub | Mechanical | Load Test | Gardens By The Bay (South) | Flower Dome |  |  |  | 2021-10-04 | 2021-10-05 |  | 2021-10-06 13:15:51 | 2021-10-06 13:16:06 | Kashvin Kaur |  |  | 0 | 0
4016 | Building | Glass Door | Classic Access Control Pte Ltd |  | [9am-5pm]Classic Access - Auto-door preventive maintenance at CM, CD, Conservatory Retail Shop, GO & CG | Building | Maintenance | Gardens By The Bay (South) | GBHQ |  |  |  | 2021-10-04 | 2021-10-08 |  | 2021-10-09 16:31:53 | 2021-10-09 16:32:06 | Kashvin Kaur |  |  | 0 | 0
4017 | Building | Glass Door | Classic Access Control Pte Ltd |  | [9am-5pm]Classic Access - Auto-door preventive maintenance at FF & Retail Shop | Building | Maintenance | Gardens By The Bay (South) | Floral Fantasy |  |  |  | 2021-10-11 | 2021-10-11 |  | 2021-10-12 11:01:36 | 2021-10-12 11:11:38 | Kashvin Kaur |  |  | 0 | 0
4019 | Building | PA | Test Company |  | [8.30am-6pm]Electronics & Engineering - Audio visual maintenance FD Event Hall, Waterview, CF, ST, CG, Gift Shop, Meeting Room, FF | Building | Maintenance | Gardens By The Bay (South) | Floral Fantasy |  |  |  | 2021-10-04 | 2021-10-17 |  | 2021-10-18 11:46:32 | 2021-10-18 11:46:47 | Kashvin Kaur |  |  | 0 | 0
4020 | Telecommunication | Troubleshooting | M1 |  | [9am-4.30pm]Soon PohTelecommunications - Maintenance Work at M1 BTS Location inside MDF Room | Telecommunication | Maintenance | Gardens By The Bay (South) | Energy Centre |  |  |  | 2021-10-01 | 2021-10-01 |  | 2021-10-02 12:06:12 | 2021-10-02 12:06:48 | Kashvin Kaur |  |  | 0 | 0
4023 | Electrical | Cable and Trunking | Test Company |  | [9am-12am]Singapore District Cooling - Cable Laying and Installation of New Change-over & switch for RTU Panel In Heat-Exchanger Rooms. | Electrical | Installation | Gardens By The Bay (South) | Bayfront |  |  |  | 2021-10-04 | 2021-10-11 |  | 2021-10-12 11:00:54 | 2021-10-12 11:01:10 | Kashvin Kaur |  |  | 0 | 0
4024 | Building | Structural | Ken-Pal Pte Ltd |  | [9am-6pm]Ken-Pal-Construction works for Bayfront Shuttle | Building | Construction | Gardens By The Bay (South) | Bayfront |  |  |  | 2021-09-28 | 2022-01-31 | [6 empty] | 0 | 0
4037 | Building | Ceiling | Ken-Pal Pte Ltd |  | [8pm-6am]KenPal - Ceiling board replacement at Floral Fantasy | Building | Replacement | Gardens By The Bay (South) | Floral Fantasy |  |  |  | 2021-09-29 | 2021-10-27 |  | 2021-10-28 11:54:29 | 2021-10-28 11:54:48 | Kashvin Kaur |  |  | 0 | 0
4038 | Electrical | Light Bulb | Kurihara Kogyo Co. Ltd |  | 9am-6pm]Kurihara - Replacement of faulty 6m lamp pole at Silver Garden | Electrical | Replacement | Gardens By The Bay (South) | Silver Garden |  |  |  | 2021-09-30 | 2021-10-01 |  | 2021-10-02 12:05:35 | 2021-10-02 12:05:49 | Kashvin Kaur |  |  | 0 | 0
4039 | Electrical | Light Fitting | SMM Pte Ltd |  | [9am-7am]SMM M&E - Retrofitting of LED lights and installation of timers at Arrival & Floral Fantasy | Electrical | Retrofitting | Gardens By The Bay (South) | Floral Fantasy |  |  |  | 2021-10-01 | 2021-10-31 |  | 2021-11-01 12:48:23 | 2021-11-01 12:48:36 | Kashvin Kaur |  |  | 0 | 0
4042 | Mechanical | Lift System | OTIS Singapore Co Pte Ltd |  | [8am-5pm]Otis lift servicing - MGL1, MGL2 | Mechanical | Servicing | Gardens By The Bay (South) | Other Outdoor Area |  |  |  | 2021-10-01 | 2021-10-01 |  | 2021-10-02 10:45:23 | 2021-10-02 10:45:36 | Kashvin Kaur |  |  | 0 | 0
4043 | Mechanical | Riser | Test Company |  | [7.30am-5.30pm]Christensen Irrigation - Irrigation maintenance works at CM Conservatory | Mechanical | Maintenance | Gardens By The Bay (South) | Cloud Forest |  |  |  | 2021-10-04 | 2021-10-08 |  | 2021-10-09 15:21:28 | 2021-10-09 15:24:46 | Kashvin Kaur |  |  | 0 | 0
4044 | Building | Pipe | Test Company |  | [9pm-6am]SMM M&E - Pipe laying and connection works at Silver Garden | Building | Laying | Gardens By The Bay (South) | Silver Garden |  |  |  | 2021-09-30 | 2021-10-30 |  | 2021-11-01 13:21:03 | 2021-11-01 13:21:17 | Kashvin Kaur |  |  | 0 | 0
4045 | Events | VIP Event / Visitation | Test Company |  | [6.30pm-8pm]VIP Visit : To isolate PA & switch on lantern lights for indoor & outdoor | Events | Isolate | Gardens By The Bay (South) | Other Outdoor Area |  |  |  | 2021-10-01 | 2021-10-02 |  | 2021-10-04 13:31:45 | 2021-10-04 13:31:59 | Kashvin Kaur |  |  | 0 | 0
4047 | Building | PA | Test Company |  | [9am-6pm]Iceberg X - Onsite installation at Cloud Forest and Flower Dome server room | Building | Installation | Gardens By The Bay (South) | Flower Dome |  |  |  | 2021-10-01 | 2021-10-07 |  | 2021-10-09 14:43:06 | 2021-10-09 14:44:26 | Kashvin Kaur |  |  | 0 | 0
4048 | Events | Event Setup | Test Company |  | [8am-9.30am]Setup of stage for Internal Wedding Photoshoot at Flower Field Hall | Events | Photoshoot | Gardens By The Bay (South) | Flower Dome |  |  |  | 2021-10-05 | 2021-10-05 |  | 2021-10-06 13:16:25 | 2021-10-06 13:16:41 | Kashvin Kaur |  |  | 0 | 0
4049 | Events | Workshop | Test Company |  | [9am-7pm]Get Crafty! Partner-led Australian Garden Weekend Workshops | Events | Crafty | Gardens By The Bay (South) | Flower Dome |  |  |  | 2021-10-30 | 2021-12-05 | [6 empty] | 0 | 0
4050 | Mechanical | Air Conditioning System | Taikisha Pte Ltd |  | [8.30am-10pm]Taikisha - BMS Enhancement works | Mechanical | Enhancement | Gardens By The Bay (South) | Energy Centre |  |  |  | 2021-10-04 | 2021-10-08 |  | 2021-10-09 16:11:33 | 2021-10-09 16:27:15 | Kashvin Kaur |  |  | 0 | 0
4051 | Building | Structural | Test Company |  | [10pm-7am]Universal Displays - Install banners on lamp post & pillars at Collonade & Canopy | Building | Installation | Gardens By The Bay (South) | Canopy Hub |  |  |  | 2021-10-05 | 2021-10-06 |  | 2021-10-07 13:25:11 | 2021-10-07 13:25:27 | Kashvin Kaur |  |  | 0 | 0
4053 | Mechanical | Fire Alarm / Detection System | Firetronics Pte Ltd |  | [9am-7pm]Firetronics - Fire alarm system maintenance at various locations | Mechanical | Maintenance | Gardens By The Bay (South) | BMS Room |  |  |  | 2021-10-04 | 2021-10-06 |  | 2021-10-07 13:24:05 | 2021-10-07 13:24:20 | Kashvin Kaur |  |  | 0 | 0
4055 | Building Security System | VESDA System | Test Company |  | [9am-6pm]Bes Tech - VESDA servicing & maintenance work at CF & FD | Building Security System | Maintenance | Gardens By The Bay (South) | Cloud Forest |  |  |  | 2021-10-05 | 2021-10-05 |  | 2021-10-06 14:09:49 | 2021-10-06 14:10:18 | Kashvin Kaur |  |  | 0 | 0
4056 | Electrical | Light Fitting | Kurihara Kogyo Co. Ltd |  | [8.30am-5.30pm]Kurihara - East pit change the location at Bayfront Shuttle Service | Electrical | Change | Gardens By The Bay (South) | Bayfront |  |  |  | 2021-10-04 | 2021-10-04 |  | 2021-10-05 15:31:49 | 2021-10-05 15:32:03 | Kashvin Kaur |  |  | 0 | 0
4057 | Events | Wedding | Test Company |  | [11.45am-11.15pm]Wedding Reception of Mr Khaja's Daughter at FFH & Magnolia Room | Events | Reception | Gardens By The Bay (South) | Flower Dome |  |  |  | 2021-10-09 | 2021-10-09 |  | 2021-10-11 13:29:36 | 2021-10-11 13:30:01 | Kashvin Kaur |  |  | 0 | 0
4058 | Events | Wedding | Test Company |  | [3pm-8pm]Wedding Solemnization of Mr Lim Wai Kit and Ms Wong Peek Hui at Supertree Observatory | Events | Solemnization | Gardens By The Bay (South) | Supertree Grove |  |  |  | 2021-10-10 | 2021-10-10 |  | 2021-10-11 15:13:50 | 2021-10-11 15:14:05 | Kashvin Kaur |  |  | 0 | 0
4061 | Mechanical | Air Conditioning System | Taikisha Pte Ltd |  | [8.30am-10pm]Taikisha - Weekly maintenance of ACMV and BMS system | Mechanical | Maintenance | Gardens By The Bay (South) | Energy Centre |  |  |  | 2021-10-04 | 2021-10-10 |  | 2021-10-11 13:33:46 | 2021-10-11 13:36:03 | Kashvin Kaur |  |  | 0 | 0
4062 | Electrical | LED Lights | Kurihara Kogyo Co. Ltd |  | [8.30am-5.30pm]Kurihara - Installation of rooting and 3.5m lamp pole at Canopy behind | Electrical | Installation | Gardens By The Bay (South) | Canopy Hub |  |  |  | 2021-10-05 | 2021-10-07 |  | 2021-10-09 15:44:37 | 2021-10-09 15:44:50 | Kashvin Kaur |  |  | 0 | 0
4063 | Building | Building External Surfaces | Test Company |  | [8.30am-5.30pm]AEG - Shade maintenance at FD LT Switch room | Building | Maintenance | Gardens By The Bay (South) | Flower Dome |  |  |  | 2021-10-06 | 2021-10-12 |  | 2021-10-13 16:50:14 | 2021-10-13 16:50:31 | Kashvin Kaur |  |  | 0 | 0
4064 | Electrical | LED Lights | Kurihara Kogyo Co. Ltd |  | [9am-9pm]Kurihara - Replacement of 5M & 6M lamp poles at Meadow carparkand Coachpark | Electrical | Replacement | Gardens By The Bay (South) | Meadow |  |  |  | 2021-10-06 | 2021-10-08 |  | 2021-10-09 16:54:44 | 2021-10-09 17:03:03 | Kashvin Kaur |  |  | 0 | 0
4065 | Mechanical | Lift System | OTIS Singapore Co Pte Ltd |  | [8am-5pm]Otis lift servicing - HBFL2 | Mechanical | Servicing | Gardens By The Bay (South) | Canopy Hub |  |  |  | 2021-10-04 | 2021-10-04 |  | 2021-10-07 14:35:09 | 2021-10-07 14:35:28 | Kashvin Kaur |  |  | 0 | 0
4066 | Mechanical | Lift System | OTIS Singapore Co Pte Ltd |  | [8am-5pm]Otis lift servicing - CMFL4 | Mechanical | Servicing | Gardens By The Bay (South) | Cloud Forest |  |  |  | 2021-10-05 | 2021-10-05 |  | 2021-10-07 14:36:30 | 2021-10-07 14:36:46 | Kashvin Kaur |  |  | 0 | 0
4067 | Mechanical | Lift System | OTIS Singapore Co Pte Ltd |  | [8am-5pm]Otis lift servicing - HBFL5 | Mechanical | Servicing | Gardens By The Bay (South) | Canopy Hub |  |  |  | 2021-10-06 | 2021-10-06 |  | 2021-10-07 14:38:30 | 2021-10-07 14:40:04 | Kashvin Kaur |  |  | 0 | 0
4068 | Mechanical | Lift System | OTIS Singapore Co Pte Ltd |  | [8am-5pm]Otis lift servicing - CMFL5 | Mechanical | Servicing | Gardens By The Bay (South) | Cloud Forest |  |  |  | 2021-10-07 | 2021-10-07 |  | 2021-10-09 16:48:23 | 2021-10-09 16:48:36 | Kashvin Kaur |  |  | 0 | 0
4069 | Electrical | LED Lights | Kurihara Kogyo Co. Ltd |  | [3pm-5.30pm]Kurihara - Replacement of down lights at Floral Fantasy walk way | Electrical | Replacement | Gardens By The Bay (South) | Floral Fantasy |  |  |  | 2021-10-07 | 2021-10-08 |  | 2021-10-09 16:47:04 | 2021-10-09 16:47:20 | Kashvin Kaur |  |  | 0 | 0
4070 | Electrical | STBY / Base Load Generator | SMM Pte Ltd |  | [9am-6pm]SMM M&E - Topping up of diesel for standby generators at Service Road, Meadow & Padang | Electrical | Replacement | Gardens By The Bay (South) | Meadow |  |  |  | 2021-10-08 | 2021-10-09 |  | 2021-10-11 11:46:25 | 2021-10-11 11:52:31 | Kashvin Kaur |  |  | 0 | 0
4071 | Events | Workshop | Test Company |  | [2pm-4.15pm]Colours in Bloom Deluxe: Hanging Floral Sphere Onsite Workshop at Ficus Room | Events | Onsite | Gardens By The Bay (South) | Active Garden |  |  |  | 2021-10-09 | 2021-10-09 |  | 2021-10-11 14:56:44 | 2021-10-11 14:57:00 | Kashvin Kaur |  |  | 0 | 0
4072 | Telecommunication | Climate | Starhub |  | [9am-6pm]Chirsty Bee Teck International - Recovery of unused Starhub Equipment inside MDF room | Telecommunication | Recovery | Gardens By The Bay (South) | Energy Centre |  |  |  | 2021-10-14 | 2021-10-16 |  | 2021-10-18 11:52:40 | 2021-10-18 11:52:53 | Kashvin Kaur |  |  | 0 | 0
4073 | Events | Event Setup | Test Company |  | [8am-6pm]Blue Sky Events - Setup/Teardown of Christmas Wonderland 2021 at Various Locations | Events | Setup/Teardown | Gardens By The Bay (South) | Flower Dome |  |  |  | 2021-10-11 | 2022-01-28 | [6 empty] | 0 | 0
4074 | Mechanical | Air Conditioning System | Taikisha Pte Ltd |  | [8am-10pm]Taikisha - Weekly maintenance of ACMV & BMS system | Mechanical | Maintenance | Gardens By The Bay (South) | Energy Centre |  |  |  | 2021-10-11 | 2021-10-17 |  | 2021-10-18 11:51:23 | 2021-10-18 11:51:39 | Kashvin Kaur |  |  | 0 | 0
4075 | Events | Wedding | Test Company |  | [4pm-9pm]Wedding Solemnization of Mr Arry Adrian Arifin Arkarphyo at Supertree Observatory | Events | Solemnization | Gardens By The Bay (South) | Supertree Grove |  |  |  | 2021-10-22 | 2021-10-22 |  | 2021-10-23 09:58:19 | 2021-10-23 10:00:07 | Kashvin Kaur |  |  | 0 | 0
4076 | Electrical | Cable and Trunking | SMM Pte Ltd |  | [8am-8pm]SMM M&E - Cable laying and termination at new 200A OG Box at Kingfisher Lake | Electrical | Laying | Gardens By The Bay (South) | Satay by the Garden |  |  |  | 2021-10-11 | 2021-10-20 |  | 2021-10-21 11:51:24 | 2021-10-21 11:51:40 | Kashvin Kaur |  |  | 0 | 0
4078 | Electrical | Cable and Trunking | Test Company |  | [8am-6pm]TTJ Design - Inspection and maintenance work at Aeriel Walkway cable connectors | Electrical | Inspection | Gardens By The Bay (South) | Supertree Grove |  |  |  | 2021-10-18 | 2021-10-19 |  | 2021-10-20 11:59:10 | 2021-10-20 11:59:24 | Kashvin Kaur |  |  | 0 | 0
4080 | Events | Wedding | Test Company |  | [5.30m-7.30pm]Wedding Proposal of Mr Tony Tay at Supertree Observatory | Events | Proposal | Gardens By The Bay (South) | Supertree Grove |  |  |  | 2021-10-25 | 2021-10-25 |  | 2021-10-26 14:45:46 | 2021-10-26 14:48:37 | Kashvin Kaur |  |  | 0 | 0
4081 | Mechanical | Fire Alarm / Detection System | RICO Engineering Works Pte Ltd |  | [9am-6pm]Rico Engineering - Routine servicing for fire alarm system, hosereel system, sprinkler system & FM200 system | Mechanical | Servicing | Gardens By The Bay (South) | Service Tunnel |  |  |  | 2021-10-19 | 2021-10-19 |  | 2021-10-20 18:52:07 | 2021-10-20 18:52:23 | Kashvin Kaur |  |  | 0 | 0
4082 | Plumbing & Sanitary | Tap | Test Company |  | [9am-6pm]SMM M&E - Repair of Water Dispenser at Floral Fantasy | Plumbing & Sanitary | Repair | Gardens By The Bay (South) | Floral Fantasy |  |  |  | 2021-10-14 | 2021-10-15 |  | 2021-10-16 10:48:05 | 2021-10-16 10:48:22 | Kashvin Kaur |  |  | 0 | 0
4083 | Mechanical | Chiller | SMM Pte Ltd |  | [9am-6pm]SMM M&E - Overhaul / Repair of Chilled Water Pump at EC Chiller Plant Room | Mechanical | Repair | Gardens By The Bay (South) | Energy Centre |  |  |  | 2021-10-14 | 2021-10-15 |  | 2021-10-16 10:47:24 | 2021-10-16 10:47:37 | Kashvin Kaur |  |  | 0 | 0
4084 | Building | Building External Surfaces | Ken-Pal Pte Ltd |  | [9am-11pm]KenPal-Installation, imporvement & painting works at ST, Arrival, Bayfront and Observatory area | Building | Installation | Gardens By The Bay (South) | Supertree Grove |  |  |  | 2021-10-05 | 2021-10-16 |  | 2021-10-18 11:47:16 | 2021-10-18 11:48:58 | Kashvin Kaur |  |  | 0 | 0
4085 | Building | Building External Surfaces | Ken-Pal Pte Ltd |  | [9am-11pm]KenPal-Removal, waterproofing, painting & mock up works at Supertree, Orchid Haven | Building | Painting | Gardens By The Bay (South) | Supertree Grove |  |  |  | 2021-10-05 | 2021-10-25 |  | 2021-10-26 14:25:09 | 2021-10-26 14:26:27 | Kashvin Kaur |  |  | 0 | 0
4086 | Building | Structural | Test Company |  | [10am-6pm]AEG - Shade maintenance at FD LT Switch room | Building | Maintenance | Gardens By The Bay (South) | Flower Dome |  |  |  | 2021-10-13 | 2021-10-19 |  | 2021-10-20 11:58:08 | 2021-10-20 11:58:23 | Kashvin Kaur |  |  | 0 | 0
4087 | Mechanical | Main Hose Reel | Test Company |  | [8am-6pm]Logistics Construction - Hosereel pump and electrical maintenance at Active Garden | Mechanical | Maintenance | Gardens By The Bay (South) | Active Garden |  |  |  | 2021-10-15 | 2021-10-31 |  | 2021-11-01 11:11:23 | 2021-11-01 11:11:39 | Kashvin Kaur |  |  | 0 | 0
4088 | Building | PA | Test Company |  | [9am-6pm]Iceberg X - Onsite installation at Cloud Forest and Flower Dome server room | Building | Installation | Gardens By The Bay (South) | Flower Dome |  |  |  | 2021-10-11 | 2021-10-17 |  | 2021-10-18 11:52:02 | 2021-10-18 11:52:15 | Kashvin Kaur |  |  | 0 | 0
4089 | Events | Wedding | Test Company |  | [3pm-8pm]Wedding Proposal of Mr Aaron Teo at Supertree Observatory | Events | Proposal | Gardens By The Bay (South) | Supertree Grove |  |  |  | 2021-10-30 | 2021-10-30 |  | 2021-11-04 11:59:36 | 2021-11-04 11:59:59 | Kashvin Kaur |  |  | 0 | 0
4090 | Mechanical | Lift System | OTIS Singapore Co Pte Ltd |  | [8am-5pm]Otis lift servicing - CDBL1, CDBL2, CDBL4 | Mechanical | Servicing | Gardens By The Bay (South) | Flower Dome |  |  |  | 2021-10-08 | 2021-10-08 |  | 2021-10-14 11:40:43 | 2021-10-14 11:49:45 | Kashvin Kaur |  |  | 0 | 0
4091 | Mechanical | Lift System | OTIS Singapore Co Pte Ltd |  | [8am-5pm]Otis lift servicing - CMFL1, CMFL2 | Mechanical | Servicing | Gardens By The Bay (South) | Cloud Forest |  |  |  | 2021-10-11 | 2021-10-11 |  | 2021-10-14 11:38:56 | 2021-10-14 11:39:34 | Kashvin Kaur |  |  | 0 | 0
4092 | Mechanical | Lift System | OTIS Singapore Co Pte Ltd |  | [8am-5pm]Otis lift servicing - HBFL1, HBFL2 | Mechanical | Servicing | Gardens By The Bay (South) | Canopy Hub |  |  |  | 2021-10-13 | 2021-10-13 |  | 2021-10-14 11:39:54 | 2021-10-14 11:40:15 | Kashvin Kaur |  |  | 0 | 0
4093 | Mechanical | Lift System | OTIS Singapore Co Pte Ltd |  | [8am-5pm]Otis lift servicing - CMFL3, CMBL1 | Mechanical | Servicing | Gardens By The Bay (South) | Cloud Forest |  |  |  | 2021-10-14 | 2021-10-14 |  | 2021-10-15 10:04:56 | 2021-10-15 10:05:10 | Kashvin Kaur |  |  | 0 | 0
4094 | Telecommunication | Wireless | Test Company |  | [12am-11.59pm]Pericomp Solutions - Wifi Hotspot works at Bayfront Ticketing | Telecommunication | Installation | Gardens By The Bay (South) | Bayfront |  |  |  | 2021-10-18 | 2021-10-24 |  | 2021-10-26 14:33:47 | 2021-10-26 14:36:13 | Kashvin Kaur |  |  | 0 | 0
4096 | Telecommunication | Climate | Test Company |  | [9.30am-6pm]Xin Wen Engineering - Cleaning filter surfaces using brush/vacuum/water spray and replace faulty climate | Telecommunication | Cleaning | Gardens By The Bay (South) | Meadow |  |  |  | 2021-10-27 | 2021-10-28 |  | 2021-10-29 11:05:15 | 2021-10-30 14:23:50 | Kashvin Kaur |  |  | 0 | 0
4097 | Mechanical | Lift System | OTIS Singapore Co Pte Ltd |  | [8am-5pm]Otis lift servicing - CDFL1 | Mechanical | Servicing | Gardens By The Bay (South) | Flower Dome |  |  |  | 2021-10-15 | 2021-10-15 |  | 2021-10-16 11:05:00 | 2021-10-16 11:05:38 | Kashvin Kaur |  |  | 0 | 0
4098 | Mechanical | Kitchen Exhaust Hood System | Test Company |  | [9am-6pm]Thurst Enterprise - Servicing of kitchen equipment at Conservatory Café | Mechanical | Servicing | Gardens By The Bay (South) | Cloud Forest |  |  |  | 2021-10-15 | 2021-10-22 |  | 2021-10-23 09:57:36 | 2021-10-23 09:57:52 | Kashvin Kaur |  |  | 0 | 0
4099 | Mechanical | Chiller | SMM Pte Ltd |  | [9am-10pm]SMM M&E - ACMV PM Servicing & PM for chiller system at SB3, FF and Bay South | Mechanical | Servicing | Gardens By The Bay (South) | Floral Fantasy |  |  |  | 2021-10-16 | 2021-10-30 |  | 2021-11-04 11:57:54 | 2021-11-04 11:58:10 | Kashvin Kaur |  |  | 0 | 0
4100 | Electrical | HTLV | SMM Pte Ltd |  | [9am-6pm]SMM M&E - Electrical PM servicing at Bay South | Electrical | Servicing | Gardens By The Bay (South) | Service Tunnel |  |  |  | 2021-10-18 | 2021-10-31 |  | 2021-11-01 12:43:21 | 2021-11-01 12:43:35 | Kashvin Kaur |  |  | 0 | 0
4101 | Telecommunication | Troubleshooting | Singtel |  | [9am-6pm]Singtel lines testing at MDF room | Telecommunication | Testing | Gardens By The Bay (South) | Service Tunnel |  |  |  | 2021-10-19 | 2021-10-22 |  | 2021-10-23 10:01:03 | 2021-10-23 10:01:19 | Kashvin Kaur |  |  | 0 | 0
4102 | Events | Event Setup | Test Company |  | [9am-11.59pmpm]Hup Cheng Tentage - Tentage set-up, filming set-up and system panel at The Meadows | Events | Set-up | Gardens By The Bay (South) | Meadow |  |  |  | 2021-10-12 | 2022-01-15 | [6 empty] | 0 | 0
4106 | Mechanical | Pump | SMM Pte Ltd |  | [9am-6pm] SMM M&E - Pump PM servicing at Bay South | Mechanical | Servicing | Gardens By The Bay (South) | Other Outdoor Area |  |  |  | 2021-10-18 | 2021-10-31 |  | 2021-11-01 11:14:40 | 2021-11-01 11:14:58 | Kashvin Kaur |  |  | 0 | 0
4108 | Mechanical | Lift System | OTIS Singapore Co Pte Ltd |  | [8am-5pm]Otis lift servicing - GOL3, CPL1 | Mechanical | Servicing | Gardens By The Bay (South) | GBHQ |  |  |  | 2021-10-19 | 2021-10-19 |  | 2021-10-20 12:15:37 | 2021-10-20 12:15:51 | Kashvin Kaur |  |  | 0 | 0
4109 | Mechanical | Rain Curtain | ST Engineering Ltd |  | [8pm-11pm]ST Engineering - RWC, kinetic, projector & maintenance at Floral Fantasy | Mechanical | Servicing | Gardens By The Bay (South) | Floral Fantasy |  |  |  | 2021-10-20 | 2021-10-31 |  | 2021-11-01 11:12:13 | 2021-11-01 11:14:20 | Kashvin Kaur |  |  | 0 | 0
4110 | Building | Structural | Test Company |  | [9am-6pm]AEG - Shade maintenance at FD LT switch room | Building | Maintenance | Gardens By The Bay (South) | Flower Dome |  |  |  | 2021-10-20 | 2021-10-26 |  | 2021-10-28 12:11:18 | 2021-10-28 13:28:05 | Kashvin Kaur |  |  | 0 | 0
4111 | Mechanical | Air Conditioning System | Taikisha Pte Ltd |  | [8am-10pm]Taikisha - Weekly maintenance of ACMV and BMS system | Mechanical | Maintenance | Gardens By The Bay (South) | Energy Centre |  |  |  | 2021-10-18 | 2021-10-24 |  | 2021-10-26 14:38:17 | 2021-10-26 14:43:05 | Kashvin Kaur |  |  | 0 | 0
4112 | Building Security System | Handicapped Platform Lift | Ken-Jo Industries Pte Ltd |  | [10am-5pm]KenJo-Monthly PM for handicap lift at Flower Field Hall | Building Security System | Maintenance | Gardens By The Bay (South) | Flower Dome |  |  |  | 2021-10-22 | 2021-10-25 |  | 2021-10-26 14:43:31 | 2021-10-26 14:43:54 | Kashvin Kaur |  |  | 0 | 0
4113 | Mechanical | Roller Shutter | SMM Pte Ltd |  | [9am-6pm]SMM M&E - Replacement of synchronized motors for shading panel at Cool Nursery 3 | Mechanical | Replacement | Gardens By The Bay (South) | Cloud Forest |  |  |  | 2021-10-21 | 2021-10-29 |  | 2021-10-30 14:22:57 | 2021-10-30 14:23:20 | Kashvin Kaur |  |  | 0 | 0
4114 | Building | Drain | Power Vac Services Pte Ltd |  | [9am-6pm]Power Vac - Preventive flushing & vaccuming for sanitary & drainage lines at Outdoor & Indoor | Building | Preventive | Gardens By The Bay (South) | Other Outdoor Area |  |  |  | 2021-10-27 | 2021-11-02 |  | 2021-11-04 11:55:26 | 2021-11-04 11:55:43 | Kashvin Kaur |  |  | 0 | 0
4115 | Mechanical | Lift System | OTIS Singapore Co Pte Ltd |  | [8am-5pm]Otis lift servicing - CO5 | Mechanical | Servicing | Gardens By The Bay (South) | Supertree Grove |  |  |  | 2021-10-20 | 2021-10-20 |  | 2021-10-21 11:54:33 | 2021-10-21 11:54:49 | Kashvin Kaur |  |  | 0 | 0
4118 | Mechanical | Pump | SMM Pte Ltd |  | [9am-6pm]SMM M&E - Overhaul/Repair of chilled water pump at EC Chiller Plant Room | Mechanical | Repair | Gardens By The Bay (South) | Energy Centre |  |  |  | 2021-10-18 | 2021-10-31 |  | 2021-11-01 12:47:42 | 2021-11-01 12:47:56 | Kashvin Kaur |  |  | 0 | 0
4119 | Building | Pipe | Test Company |  | [9am-6pm]SMM M&E - Laying of water pipeline for façade cleaning outside FD | Building | Laying | Gardens By The Bay (South) | Flower Dome |  |  |  | 2021-10-22 | 2021-10-31 |  | 2021-11-01 12:43:59 | 2021-11-01 12:47:19 | Kashvin Kaur |  |  | 0 | 0
4120 | Building | Signage | Fuji Signcrafts Industries Pte Ltd |  | [8am-12am]Fuji Signcrafts - Work maintenance for signages | Building | Maintenance | Gardens By The Bay (South) | Other Outdoor Area |  |  |  | 2021-10-23 | 2021-10-30 |  | 2021-11-04 11:56:14 | 2021-11-04 11:57:09 | Kashvin Kaur |  |  | 0 | 0
4121 | Electrical | HTLV | SMM Pte Ltd |  | [9am-10pm]SMM IFM - Replacement of screws for HT & LT panel | Electrical | Replacement | Gardens By The Bay (South) | Energy Centre |  |  |  | 2021-10-22 | 2021-10-28 |  | 2021-10-29 16:58:46 | 2021-10-29 17:01:40 | Kashvin Kaur |  |  | 0 | 0
4122 | Mechanical | Pump | SMM Pte Ltd |  | [9am-6pm]SMM M&E - Installation of pump panel OGs at Chinese Garden | Mechanical | Installation | Gardens By The Bay (South) | Other Outdoor Area |  |  |  | 2021-10-22 | 2021-10-31 |  | 2021-11-01 11:15:31 | 2021-11-01 11:22:16 | Kashvin Kaur |  |  | 0 | 0
4124 | Electrical | Light Bulb | Kurihara Kogyo Co. Ltd |  | [9am-9pm]Kurihara - Replacement of 5m, 6m lamp poles at Meadow carpark and Coach Garden | Electrical | Replacement | Gardens By The Bay (South) | Meadow |  |  |  | 2021-10-23 | 2021-10-25 |  | 2021-10-26 14:44:18 | 2021-10-26 14:45:10 | Kashvin Kaur |  |  | 0 | 0
4125 | Events | Photoshoot / Media Press | Test Company |  | [6.30pm-8.05pm]PAYM 50th Anniversary Event at FFH, Waterview Room & Magnolia Room | Events | Filming | Gardens By The Bay (South) | Flower Dome |  |  |  | 2021-10-30 | 2021-10-30 |  | 2021-11-04 12:00:39 | 2021-11-04 12:02:01 | Kashvin Kaur |  |  | 0 | 0
4126 | Electrical | Light Bulb | SMM Pte Ltd |  | [9am-6pm]SMM M&E - Installation of LPS for lamp posts at Scented Walk | Electrical | Filming | Gardens By The Bay (South) | Other Outdoor Area |  |  |  | 2021-10-25 | 2021-11-24 | [6 empty] | 0 | 0
4127 | Building | Irrigation Pipe | Test Company |  | [8am-6pm]Christensen Irrigation - Irrigation maintenance at CM Conservatory Tree fern & Mountain area | Building | Maintenance | Gardens By The Bay (South) | Cloud Forest |  |  |  | 2021-10-25 | 2021-10-30 |  | 2021-11-04 12:03:53 | 2021-11-04 12:04:09 | Kashvin Kaur |  |  | 0 | 0
4128 | Mechanical | Kitchen Exhaust Hood System | Test Company |  | [9am-6pm]Thurst Enterprise - Servicing of kitchen equipment Conservatory Café/FFH Kitchen | Mechanical | Servicing | Gardens By The Bay (South) | Flower Dome |  |  |  | 2021-10-23 | 2021-10-28 |  | 2021-10-29 09:58:58 | 2021-10-29 09:59:20 | Kashvin Kaur |  |  | 0 | 0
4129 | Mechanical | Air Conditioning System | Taikisha Pte Ltd |  | [8.30am-10pm]Taikisha - Weekly maintenance of ACMV and BMS system | Mechanical | Maintenance | Gardens By The Bay (South) | Energy Centre |  |  |  | 2021-10-25 | 2021-10-31 |  | 2021-11-01 11:08:02 | 2021-11-01 11:08:16 | Kashvin Kaur |  |  | 0 | 0
4130 | Mechanical | Main Hose Reel | Test Company |  | 8am-6pm]Logistics Construction - Monthly Hose reel pump maintenance work at Active Garden | Mechanical | Maintenance | Gardens By The Bay (South) | Active Garden |  |  |  | 2021-10-27 | 2021-10-28 |  | 2021-10-30 14:24:17 | 2021-10-30 14:24:38 | Kashvin Kaur |  |  | 0 | 0
4131 | Building | Wall Hook | Ken-Pal Pte Ltd |  | [9am-6pm]Ken-Pal - Mirror installation at Supertree | Building | Installation | Gardens By The Bay (South) | Supertree Grove |  |  |  | 2021-10-23 | 2021-10-30 |  | 2021-11-04 11:58:40 | 2021-11-04 11:58:58 | Kashvin Kaur |  |  | 0 | 0
4132 | Building | Door Frame | Ken-Pal Pte Ltd |  | [8am-6pm]Ken-Pal - Installation of door and kerbs at Supertree and Active Garden | Building | Installation | Gardens By The Bay (South) | Active Garden |  |  |  | 2021-10-25 | 2021-11-06 |  | 2021-11-08 14:56:39 | 2021-11-08 14:57:02 | Kashvin Kaur |  |  | 0 | 0
4133 | Building | Structural | Ken-Pal Pte Ltd |  | [9pm-7am]Ken-Pal - Painting works at Arrival & GBHQ, Waterproofing work at Orchid Haven | Building | Painting | Gardens By The Bay (South) | GBHQ |  |  |  | 2021-10-25 | 2021-11-06 |  | 2021-11-08 15:20:19 | 2021-11-08 15:20:51 | Kashvin Kaur |  |  | 0 | 0
4134 | Events | Wedding | Test Company |  | [9pm-10pm]Wedding Proposal for Mr Scott Bustabad at OCBC Skyway | Events | Proposal | Gardens By The Bay (South) | Supertree Grove |  |  |  | 2021-10-28 | 2021-10-28 |  | 2021-10-30 14:26:39 | 2021-10-30 14:26:54 | Kashvin Kaur |  |  | 0 | 0
4135 | Building | Roof | Ken-Pal Pte Ltd |  | [9am-6pm]Ken-Pal - Female toilet sunken vanity top repair at Supertree | Building | Repair | Gardens By The Bay (South) | Supertree Grove |  |  |  | 2021-10-28 | 2021-11-15 | [6 empty] | 0 | 0
4137 | Mechanical | Lift System | OTIS Singapore Co Pte Ltd |  | [8am-5pm]Otis lift servicing - CMFL1 | Mechanical | Servicing | Gardens By The Bay (South) | Cloud Forest |  |  |  | 2021-10-26 | 2021-10-26 |  | 2021-10-30 14:21:25 | 2021-10-30 14:21:50 | Kashvin Kaur |  |  | 0 | 0
4138 | Mechanical | Lift System | OTIS Singapore Co Pte Ltd |  | [8am-5pm]Otis lift servicing - CMFL2 | Mechanical | Servicing | Gardens By The Bay (South) | Cloud Forest |  |  |  | 2021-10-27 | 2021-10-27 |  | 2021-10-28 13:33:16 | 2021-10-28 13:33:30 | Kashvin Kaur |  |  | 0 | 0
4139 | Mechanical | Lift System | OTIS Singapore Co Pte Ltd |  | [8am-5pm]Otis lift servicing - CMFL3 | Mechanical | Servicing | Gardens By The Bay (South) | Cloud Forest |  |  |  | 2021-10-28 | 2021-10-28 |  | 2021-10-30 14:25:49 | 2021-10-30 14:26:05 | Kashvin Kaur |  |  | 0 | 0
4141 | Building | Building External Surfaces | Test Company |  | [10am-5pm]AEG - Shade maintenance at FD LT switch room | Building | Maintenance | Gardens By The Bay (South) | Flower Dome |  |  |  | 2021-10-27 | 2021-11-02 |  | 2021-11-03 10:29:56 | 2021-11-03 10:30:22 | Kashvin Kaur |  |  | 0 | 0
4142 | Electrical | Lamp Post | Kurihara Kogyo Co. Ltd |  | [8.30am-5.30pm]Kurihara - Replacement of faulty light 6m lamp post at in front of Silver Garden and Coachpark | Electrical | Replacement | Gardens By The Bay (South) | Silver Garden |  |  |  | 2021-10-30 | 2021-10-30 |  | 2021-11-04 12:02:36 | 2021-11-04 12:03:11 | Kashvin Kaur |  |  | 0 | 0
4144 | Mechanical | Lift System | OTIS Singapore Co Pte Ltd |  | [8am-5pm]Otis lift servicing - CMFL4 | Mechanical | Servicing | Gardens By The Bay (South) | Cloud Forest |  |  |  | 2021-10-29 | 2021-10-29 |  | 2021-10-30 14:22:17 | 2021-10-30 14:22:31 | Kashvin Kaur |  |  | 0 | 0